CHANGE REQUEST

Workday Expenses Module

Custom Validation — Receipt Compliance Enhancement

CR-EXP-2026-007

May 2026

# 1. Change Request Overview

| CR ID | CR-EXP-2026-007 |
| --- | --- |
| Module | Expenses |
| Category | Custom Validation |
| Priority | High |
| Requested By | [Client Name / Business Owner] |
| Date Submitted | May 20, 2026 |
| Target Environment | [Sandbox / Implementation / Production] |
| Workday Version | [e.g., 2026R1] |
| Estimated Timeline | 7 weeks |

Enhance receipt validation across all existing expense items with tiered enforcement (<$25 none, $25-$75 warning, $75+ mandatory), duplicate receipt detection, and itemized receipt requirement for $250+.

# 2. Business Requirement

- AP reports a 15% rejection rate due to missing, illegible, or duplicate receipts.

- Tiered receipt rules: no receipt under $25, warning for $25-$75, mandatory for $75+.

- Duplicate receipt detection needed: same receipt image attached to a prior approved line triggers a warning.

- Itemized receipts required for any single transaction over $250.

# 3. Solution Design

- Modify global receipt requirement to tiered thresholds: <$25 none, $25-$75 soft stop, $75+ hard stop.

- Create Validation Rule 1 (CR_EXP_Receipt_Tiered_Warning): Soft stop for $25-$75 without receipt.

- Create Validation Rule 2 (CR_EXP_Receipt_Tiered_Required): Hard stop for $75+ without receipt.

- Create Validation Rule 3 (CR_EXP_Receipt_Duplicate): Hash-based duplicate check against 12 months of history.

- Create Validation Rule 4 (CR_EXP_Receipt_Itemized): Hard stop for $250+ without itemized receipt checkbox.

- Add custom checkbox 'Itemized Receipt Attached' to all expense lines.

## 3.1 Approval Workflow Impact

Unless explicitly stated above, no changes are made to the existing approval workflow. New or modified items inherit the current Expense Report approval chain.

## 3.2 Reporting Impact

New items automatically roll up into existing spend category reports. No new custom reports required unless specified.

## 3.3 Security

No new security group or domain changes required unless explicitly stated above.

## 3.4 Migration / Data Considerations

No historical data migration needed. Existing items and reports remain unaffected. All changes are forward-looking.

# 4. Test Plan

## 4.1 Test Environment & Prerequisites

Testing in Sandbox or Implementation tenant with at least 3 test workers covering eligible and ineligible scenarios. All prerequisite data must be configured before execution.

## 4.2 Tiered Receipt Rules (<$25 / $25-$75 / $75+) (Ref: 3.1 / 3.2)

| TC # | Type | Scenario | Steps | Expected Result | Ref |
| --- | --- | --- | --- | --- | --- |
| P-01 | Positive | Submit $20 without receipt | Enter $20, no receipt, submit | Submits successfully; no warning | 3.1 / 3.2 |
| P-02 | Positive | Submit $50 with receipt | Enter $50, attach receipt, submit | Submits successfully | 3.1 / 3.2 |
| P-03 | Positive | Submit $100 with receipt | Enter $100, attach receipt, submit | Submits; mandatory threshold met | 3.1 / 3.2 |
| N-01 | Negative | Submit $50 without receipt | Enter $50, no receipt, submit | Soft stop warning; can proceed | 3.1 / 3.2 |
| N-02 | Negative | Submit $100 without receipt | Enter $100, no receipt, submit | Hard stop: receipt mandatory for $75+ | 3.1 / 3.2 |
| N-03 | Negative | Boundary: $25 no receipt | Enter $25.00, no receipt, submit | Soft stop warning (at threshold) | 3.1 / 3.2 |
| N-04 | Negative | Boundary: $75 no receipt | Enter $75.00, no receipt, submit | Hard stop (at mandatory threshold) | 3.1 / 3.2 |

## 4.3 Validation Rule 3 — Duplicate Receipt Detection (Ref: 3.3)

| TC # | Type | Scenario | Steps | Expected Result | Ref |
| --- | --- | --- | --- | --- | --- |
| N-05 | Negative | Duplicate receipt submitted | Attach same receipt image used on prior approved report | Warning: receipt matches prior submission | 3.3 |

## 4.4 Validation Rule 4 — Itemized Receipt ($250+) (Ref: 3.4)

| TC # | Type | Scenario | Steps | Expected Result | Ref |
| --- | --- | --- | --- | --- | --- |
| P-04 | Positive | Submit $300 with itemized flag | Enter $300, attach receipt, check Itemized box, submit | Submits successfully | 3.4 |
| N-06 | Negative | $300 without itemized flag | Enter $300, attach receipt, Itemized unchecked, submit | Hard stop: itemized receipt required | 3.4 |

## 4.5 Regression — Existing Receipt Rules & Workflow (Ref: All)

| TC # | Type | Scenario | Steps | Expected Result | Ref |
| --- | --- | --- | --- | --- | --- |
| R-01 | Regression | Corp Card expenses unaffected | Code Corp Card transaction under $25 | No receipt required; Corp Card rules intact | All |
| R-02 | Regression | Item-level receipt rules override | Submit item with its own Always receipt rule | Item-level rule overrides global tier | All |
| R-03 | Regression | Approval workflow intact | Submit multi-line report with mixed amounts | Standard approval; no extra steps | All |

## 4.6 Test Coverage Summary

| Test Type | Count |
| --- | --- |
| Positive | 4 |
| Negative | 6 |
| Regression | 3 |
| Total | 13 |

# 5. Costing & Effort Estimate

| Activity | Role | Hours | Rate (USD/hr) | Cost (USD) |
| --- | --- | --- | --- | --- |
| Requirements Gathering & Analysis | Functional Consultant | 8 | 150 | 1,200 |
| Solution Design & Documentation | Functional Consultant | 10 | 150 | 1,500 |
| Global Receipt Rule Modification | Functional Consultant | 6 | 150 | 900 |
| Calculated Field (Hash/Duplicate) | Technical Consultant | 16 | 175 | 2,800 |
| Validation Rules (4 rules) | Functional Consultant | 10 | 150 | 1,500 |
| Custom Field Configuration | Functional Consultant | 2 | 150 | 300 |
| Unit Testing | Functional Consultant | 8 | 150 | 1,200 |
| Test Case Preparation | QA Analyst | 8 | 120 | 960 |
| UAT Support | QA Analyst | 10 | 120 | 1,200 |
| Deployment & Post-Go-Live Support | Functional Consultant | 6 | 150 | 900 |
| Project Management | Project Manager | 8 | 175 | 1,400 |
| TOTAL |  | 92 |  | 13,860 |

Estimated Timeline: 7 weeks

Notes: Rates are indicative. Effort assumes standard complexity and may vary based on tenant configuration and client UAT availability.

# 6. Rollback Plan

If critical issues arise post-deployment:

- Inactivate any new Expense Items created.

- Disable or delete all custom validation rules prefixed with the CR identifier.

- Revert any approval workflow modifications.

- Verify existing items and workflows return to pre-change behavior.

# 7. Sign-Off

| Role | Name | Date | Approval |
| --- | --- | --- | --- |
| Business Owner |  |  |  |
| Workday Functional Lead |  |  |  |
| Test Lead / QA |  |  |  |
| Change Advisory Board |  |  |  |